|  |  |  |  |
| --- | --- | --- | --- |
| ID | Description | Preceding Activity | Duration (Week) |
| A | Plans for project | none | 1 |
| B | Find all requirements | A | 2 |
| C | Designing hardware | B | 3 |
| D | Code software | B | 4 |
| E | Executing the project | D | 5 |
| F | Testing the project | E&G | 4 |
| G | Developing the project | C | 5 |

|  |  |  |
| --- | --- | --- |
| 3 | C | 6 |
| 1 | Designing | 1 |
| 4 | 3 | 7 |

|  |  |  |
| --- | --- | --- |
| 6 | G | 11 |
| 1 | developing | 1 |
| 7 | 5 | 12 |

|  |  |  |
| --- | --- | --- |
| 0 | A | 1 |
| 0 | Planning | 0 |
| 0 | 1 | 1 |

|  |  |  |
| --- | --- | --- |
| 1 | B | 3 |
| 0 | requirements | 0 |
| 1 | 2 | 3 |

|  |  |  |
| --- | --- | --- |
| 12 | F | 16 |
| 0 | Testing | 0 |
| 12 | 4 | 16 |

|  |  |  |
| --- | --- | --- |
| 3 | D | 7 |
| 0 | Coding | 0 |
| 3 | 4 | 7 |

|  |  |  |
| --- | --- | --- |
| 7 | E | 12 |
| 0 | Executing | 0 |
| 7 | 5 | 12 |